## Management Items
Unit | Rough Draft | Final Draft | Pass Test 1 | Pass Test 2 | Total | Level of Effort Items
Create Status Metric | 50% | 0% | 0% | 0% | 12.5% | Add items to Status Metric
Determine Attacks Available | 0% | 0% | 0% | 0% | 0% | Update Status Metric
Determine Map Size | 0% | 0% | 0% | 0% | 0%
Determine Map Boundary | 0% | 0% | 0% | 0% | 0%
Determine Zoom Level | 0% | 0% | 0% | 0% | 0%
Determine Sprite to Map Size Ratio | 0% | 0% | 0% | 0% | 0%
Determine Items | 0% | 0% | 0% | 0% | 0%
Determine naming convention (champs/heroes/etc.) | 0% | 0% | 0% | 0% | 0%

## Code Items
| Unit | Rough Draft | Final Draft | Pass Test 1 | Pass Test 2 | Total
Movement | World Collision | 100% | 100% | 0% | 0% | 50%
| Jumping | 100% | 100% | 0% | 0% | 50%
| Gravity | 100% | 100% | 0% | 0% | 50%
| Jumping onto Slopes | 100% | 100% | 0% | 0% | 50%
| Jumping off of Slopes | 100% | 100% | 0% | 0% | 50%
| Ascending Slopes | 100% | 100% | 0% | 0% | 50%
| Descending Slopes | 0% | 0% | 0% | 0% | 0%
| Wall jumping | 0% | 0% | 0% | 0% | 0%
| Wall sliding | 0% | 0% | 0% | 0% | 0%
| Moving platforms | 0% | 0% | 0% | 0% | 0%
| Character on platform | 0% | 0% | 0% | 0% | 0%
State Transition | Idle Right | 100% | 0% | 0% | 0% | 25%
| Idle Left | 0% | 0% | 0% | 0% | 0%
| Turning | 0% | 0% | 0% | 0% | 0%
| Crouch Right | 0% | 0% | 0% | 0% | 0%
| Crouch Left | 0% | 0% | 0% | 0% | 0%
| Walking Right | 0% | 0% | 0% | 0% | 0%
| Walking Left | 0% | 0% | 0% | 0% | 0%
| Running Right | 0% | 0% | 0% | 0% | 0%
| Running Left | 0% | 0% | 0% | 0% | 0%
| Jump Up | 0% | 0% | 0% | 0% | 0%
| Jump Right | 0% | 0% | 0% | 0% | 0%
| Jump Left | 0% | 0% | 0% | 0% | 0%
| Skill 1 Right | 0% | 0% | 0% | 0% | 0%
| Skill 1 Left | 0% | 0% | 0% | 0% | 0%
| Skill 2 Right | 0% | 0% | 0% | 0% | 0%
| Skill 2 Left | 0% | 0% | 0% | 0% | 0%
| Skill 3 Right | 0% | 0% | 0% | 0% | 0%
| Skill 3 Left | 0% | 0% | 0% | 0% | 0%
| Skill 4 Right | 0% | 0% | 0% | 0% | 0%
| Skill 4 Left | 0% | 0% | 0% | 0% | 0%
| Attack Upright | 0% | 0% | 0% | 0% | 0%
| Attack Right | 0% | 0% | 0% | 0% | 0%
| Attack Downright | 0% | 0% | 0% | 0% | 0%
| Attack Down | 0% | 0% | 0% | 0% | 0%
| Attack Downleft | 0% | 0% | 0% | 0% | 0%
| Attack Left | 0% | 0% | 0% | 0% | 0%
| Attack Upleft | 0% | 0% | 0% | 0% | 0%
| Attack Up | 0% | 0% | 0% | 0% | 0%
| Run Attack Right | 0% | 0% | 0% | 0% | 0%
| Run Attack Left | 0% | 0% | 0% | 0% | 0%
| Wall Crouch Right | 0% | 0% | 0% | 0% | 0%
| Wall Crouch Left | 0% | 0% | 0% | 0% | 0%
| Wall Jump Right | 0% | 0% | 0% | 0% | 0%
| Wall Jump Left | 0% | 0% | 0% | 0% | 0%
| Air Attack Right | 0% | 0% | 0% | 0% | 0%
| Air Attack Down | 0% | 0% | 0% | 0% | 0%
| Air Attack Left | 0% | 0% | 0% | 0% | 0%
| Air Attack Up | 0% | 0% | 0% | 0% | 0%

## Art Items
| Unit | Rough Draft | Final Draft | Pass Test 1 | Pass Test 2 | Total
Hidekage | Sprite Sheet | 0% | 0% | 0% | 0% | 0%
| Still | 100% | 0% | 0% | 0% | 25%
| Idle Right | 100% | 0% | 0% | 0% | 25%
| Idle Left | 0% | 0% | 0% | 0% | 0%
| Turning | 0% | 0% | 0% | 0% | 0%
| Crouch Right | 0% | 0% | 0% | 0% | 0%
| Crouch Left | 0% | 0% | 0% | 0% | 0%
| Walking Right | 0% | 0% | 0% | 0% | 0%
| Walking Left | 0% | 0% | 0% | 0% | 0%
| Running Right | 0% | 0% | 0% | 0% | 0%
| Running Left | 0% | 0% | 0% | 0% | 0%
| Jump Up | 0% | 0% | 0% | 0% | 0%
| Jump Right | 0% | 0% | 0% | 0% | 0%
| Jump Left | 0% | 0% | 0% | 0% | 0%
| Skill 1 Right | 0% | 0% | 0% | 0% | 0%
| Skill 1 Left | 0% | 0% | 0% | 0% | 0%
| Skill 2 Right | 0% | 0% | 0% | 0% | 0%
| Skill 2 Left | 0% | 0% | 0% | 0% | 0%
| Skill 3 Right | 0% | 0% | 0% | 0% | 0%
| Skill 3 Left | 0% | 0% | 0% | 0% | 0%
| Skill 4 Right | 0% | 0% | 0% | 0% | 0%
| Skill 4 Left | 0% | 0% | 0% | 0% | 0%
| Attack Upright | 0% | 0% | 0% | 0% | 0%
| Attack Right | 0% | 0% | 0% | 0% | 0%
| Attack Downright | 0% | 0% | 0% | 0% | 0%
| Attack Down | 0% | 0% | 0% | 0% | 0%
| Attack Downleft | 0% | 0% | 0% | 0% | 0%
| Attack Left | 0% | 0% | 0% | 0% | 0%
| Attack Upleft | 0% | 0% | 0% | 0% | 0%
| Attack Up | 0% | 0% | 0% | 0% | 0%
| Run Attack Right | 0% | 0% | 0% | 0% | 0%
| Run Attack Left | 0% | 0% | 0% | 0% | 0%
| Wall Crouch Right | 0% | 0% | 0% | 0% | 0%
| Wall Crouch Left | 0% | 0% | 0% | 0% | 0%
| Wall Jump Right | 0% | 0% | 0% | 0% | 0%
| Wall Jump Left | 0% | 0% | 0% | 0% | 0%
| Air Attack Right | 0% | 0% | 0% | 0% | 0%
| Air Attack Down | 0% | 0% | 0% | 0% | 0%
| Air Attack Left | 0% | 0% | 0% | 0% | 0%
| Air Attack Up | 0% | 0% | 0% | 0% | 0%
Layton | Sprite Sheet | 0% | 0% | 0% | 0% | 0%
| Still | 100% | 0% | 0% | 0% | 25%
| Idle Right | 100% | 0% | 0% | 0% | 25%
| Idle Left | 0% | 0% | 0% | 0% | 0%
| Turning | 0% | 0% | 0% | 0% | 0%
| Crouch Right | 0% | 0% | 0% | 0% | 0%
| Crouch Left | 0% | 0% | 0% | 0% | 0%
| Walking Right | 0% | 0% | 0% | 0% | 0%
| Walking Left | 0% | 0% | 0% | 0% | 0%
| Running Right | 0% | 0% | 0% | 0% | 0%
| Running Left | 0% | 0% | 0% | 0% | 0%
| Jump Up | 0% | 0% | 0% | 0% | 0%
| Jump Right | 0% | 0% | 0% | 0% | 0%
| Jump Left | 0% | 0% | 0% | 0% | 0%
| Skill 1 Right | 0% | 0% | 0% | 0% | 0%
| Skill 1 Left | 0% | 0% | 0% | 0% | 0%
| Skill 2 Right | 0% | 0% | 0% | 0% | 0%
| Skill 2 Left | 0% | 0% | 0% | 0% | 0%
| Skill 3 Right | 0% | 0% | 0% | 0% | 0%
| Skill 3 Left | 0% | 0% | 0% | 0% | 0%
| Skill 4 Right | 0% | 0% | 0% | 0% | 0%
| Skill 4 Left | 0% | 0% | 0% | 0% | 0%
| Attack Upright | 0% | 0% | 0% | 0% | 0%
| Attack Right | 0% | 0% | 0% | 0% | 0%
| Attack Downright | 0% | 0% | 0% | 0% | 0%
| Attack Down | 0% | 0% | 0% | 0% | 0%
| Attack Downleft | 0% | 0% | 0% | 0% | 0%
| Attack Left | 0% | 0% | 0% | 0% | 0%
| Attack Upleft | 0% | 0% | 0% | 0% | 0%
| Attack Up | 0% | 0% | 0% | 0% | 0%
| Run Attack Right | 0% | 0% | 0% | 0% | 0%
| Run Attack Left | 0% | 0% | 0% | 0% | 0%
| Wall Crouch Right | 0% | 0% | 0% | 0% | 0%
| Wall Crouch Left | 0% | 0% | 0% | 0% | 0%
| Wall Jump Right | 0% | 0% | 0% | 0% | 0%
| Wall Jump Left | 0% | 0% | 0% | 0% | 0%
| Air Attack Right | 0% | 0% | 0% | 0% | 0%
| Air Attack Down | 0% | 0% | 0% | 0% | 0%
| Air Attack Left | 0% | 0% | 0% | 0% | 0%
| Air Attack Up | 0% | 0% | 0% | 0% | 0%
Loganman | Sprite Sheet | 0% | 0% | 0% | 0% | 0%
| Still | 100% | 0% | 0% | 0% | 25%
| Idle Right | 100% | 0% | 0% | 0% | 25%
| Idle Left | 0% | 0% | 0% | 0% | 0%
| Turning | 0% | 0% | 0% | 0% | 0%
| Crouch Right | 0% | 0% | 0% | 0% | 0%
| Crouch Left | 0% | 0% | 0% | 0% | 0%
| Walking Right | 0% | 0% | 0% | 0% | 0%
| Walking Left | 0% | 0% | 0% | 0% | 0%
| Running Right | 0% | 0% | 0% | 0% | 0%
| Running Left | 0% | 0% | 0% | 0% | 0%
| Jump Up | 0% | 0% | 0% | 0% | 0%
| Jump Right | 0% | 0% | 0% | 0% | 0%
| Jump Left | 0% | 0% | 0% | 0% | 0%
| Skill 1 Right | 0% | 0% | 0% | 0% | 0%
| Skill 1 Left | 0% | 0% | 0% | 0% | 0%
| Skill 2 Right | 0% | 0% | 0% | 0% | 0%
| Skill 2 Left | 0% | 0% | 0% | 0% | 0%
| Skill 3 Right | 0% | 0% | 0% | 0% | 0%
| Skill 3 Left | 0% | 0% | 0% | 0% | 0%
| Skill 4 Right | 0% | 0% | 0% | 0% | 0%
| Skill 4 Left | 0% | 0% | 0% | 0% | 0%
| Attack Upright | 0% | 0% | 0% | 0% | 0%
| Attack Right | 0% | 0% | 0% | 0% | 0%
| Attack Downright | 0% | 0% | 0% | 0% | 0%
| Attack Down | 0% | 0% | 0% | 0% | 0%
| Attack Downleft | 0% | 0% | 0% | 0% | 0%
| Attack Left | 0% | 0% | 0% | 0% | 0%
| Attack Upleft | 0% | 0% | 0% | 0% | 0%
| Attack Up | 0% | 0% | 0% | 0% | 0%
| Run Attack Right | 0% | 0% | 0% | 0% | 0%
| Run Attack Left | 0% | 0% | 0% | 0% | 0%
| Wall Crouch Right | 0% | 0% | 0% | 0% | 0%
| Wall Crouch Left | 0% | 0% | 0% | 0% | 0%
| Wall Jump Right | 0% | 0% | 0% | 0% | 0%
| Wall Jump Left | 0% | 0% | 0% | 0% | 0%
| Air Attack Right | 0% | 0% | 0% | 0% | 0%
| Air Attack Down | 0% | 0% | 0% | 0% | 0%
| Air Attack Left | 0% | 0% | 0% | 0% | 0%
| Air Attack Up | 0% | 0% | 0% | 0% | 0%

## Version Tracker
Builds | [5 empty] | Milestones
Software Version |  |  |  |  | Update | Phase | Version | Major update
0 | . | 1 | . | 0 | Character and map integration | Development | 0.1.0 | Character and map integration
| . |  | . |  |  | Development | 0.2.0 | Hitboxes developed
| . |  | . |  |  | Development | 0.3.0 | Feature development/objectives
| . |  | . |  |  | Development | 0.4.0 | GUI developed
| . |  | . |  |  | Alpha | 0.5.0 | Networking code developed
| . |  | . |  |  | Alpha | 0.6.0
| . |  | . |  |  | Alpha | 0.7.0
| . |  | . |  |  | Alpha | 0.8.0
| . |  | . |  |  | Beta | 0.9.0 | 20 characters developed
| . |  | . |  |  | Full | 1.0.0 | Steam release
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .
| . |  | .